## Foglio1
Purchase order 31381147: Ex F Product training development - Fixe | [6 empty] | 238500
Month | ACTIVITY | DAYS | COST X DAY (€) | TOTAL | MANAGER | BUDGET (€) | PRICE (€) | APPROVAL |  | GOOD RECEPTIONS (GR) |  | REMARKS
[8 empty] | who | When | Amount (€) | Data
| Invoice KOINE 013/2025 | [5 empty] | 35268.26
January-February-March | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 1st quarter 2025 |  |  |  | 80000 | 20000
January-February-March | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 42 | 363.53 | 15268.26 | D'Aquino | 80000 | 15268.26
| Invoice KOINE 015/2025 | [5 empty] | 12288.66
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17 | 295.18 | 5018.06 | D'Aquino | 80000 | 5018.06 | [5 empty] | 17
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 20 | 363.53 | 7270.6 | Barbirato | 80000 | 7270.6 | [5 empty] | 20
| Invoice KOINE 019/2025 | [5 empty] | 71692.69
April-May-June | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 2nd quarter 2025 |  |  |  |  | 20000
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17+20+23 | 295.18 | 17710.8 | D'Aquino |  | 17710.8 | [5 empty] | 60
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 17+20+20 | 363.53 | 20721.21 | Barbirato |  | 20721.21 | [5 empty] | 57
| 2nd quarter total | [5 empty] | 58432.01
| Remaining amount from invoice 019/2025 | [5 empty] | 13260.68
| Total order remaining amount | [5 empty] | 119250.39

## Fixed cost exF+50% Transv
GLOBAL PROGRAM OFFICE
Job Title | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 1 SENIOR PROJECT MANAGEMENT ACTIVITY | Total
Customer Facing (Yes) | Yes | Yes
Full Time Equivalent % | 50% | 100%
Cost per person per day (on the basis of 218 working days) | 366.9725 | 363.5321
Fixed Cost Total | 80000 | 79250 | 159250
Job Title | SENIOR PROJECT MANAGEMENT ACTIVITY - OPTIONAL | 1 JUNIOR TRAINING SPECIALIST ACTIVITY - OPTIONAl | 1 JUNIOR TRAINING SPECIALIST ACTIVITY - OPTIONAL | Total
Customer Facing (Yes) | Yes | Yes | Yes
Full Time Equivalent % | 100% | 100% | 100%
Cost per person per day (on the basis of 218 working days) | 363.5321 | 295.1835 | 295.1835
Fixed Cost Total | 79250 | 64350 | 64350 | 207950 | 367200
SUPPORTING ROLES Included in deliverables cost
Job Title | 4 PROJECT MANAGERS (COORDINATORS) | AGENCY INTERNAL EXPERT | 3rd PARTY EXPERTS
Customer Facing ( Yes) | yes | yes
Full Time Equivalent % | 100% | 100%
Total Cost Fixed | 0 | 0
If needed ; Variable Cost per day