## PLANNING 2025
2025 COURSE PLANNING
KEY
Materials
Storyboarding
M | Meeting in progress
Articulate development
Final approval
Delivery to Stellantis
| Month | [17 empty] | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER | [29 empty] | JANUARY 2026
| Week |  |  |  | 52 | [6 empty] | 1 | [11 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 53
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | W | T | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S
SALES METHOD
Materials (first part)
Paper version
Articulate development
Translation and Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL NPS
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Fiat 500 - 600 - Pandina new trim strategy (D'Aquino)
Materials
Storyboarding and Synthesia development
Capsule development
Final approval
Delivery to Stellantis
LANCIA 8 YEARS WARRANTY capsule
Materials
| Storyboarding | [136 empty] | M
Capsule development
Final approval
Delivery to Stellantis
ALFA ROMEO NEW TONALE WBT 1
Materials (Instruction letter)
| Storyboarding | [136 empty] | M | [75 empty] | M
Articulate development
Final approval
Delivery to Stellantis
PUBLIC CHARGING (Lerch) Part 2 WBT
Instruction letter december 2024
Storyboarding
Articulate development
| Meeting in progress | [33 empty] | M
Final approval
Delivery to Stellantis
AMI WBT (D'Aquino)
Materials
| Storyboarding | [45 empty] | M | [11 empty] | M
| Articulate development | [107 empty] | M
Final approval
Delivery to Stellantis
JEEP NEW COMPASS WBT - Part 1 (Barbirato)
Instruction letter december 2024
| Storyboarding | [23 empty] | M | [6 empty] | M | [7 empty] | M |  | M | [16 empty] | M
Articulate development
Final approval
Delivery to Stellantis
LANCIA YPSILON HF WBT (Barbirato)
Instruction letter 2024/11/22
| Storyboarding | [25 empty] | M |  |  |  | M |  |  |  | M |  |  |  | M |  | M | [5 empty] | M
Articulate development
Final approval
Delivery to Stellantis
Fiat TRIS WBT
Material - January 29
| Storyboarding | [103 empty] | M | [13 empty] | M | [11 empty] | M | [15 empty] | M | [6 empty] | M
Articulate development
Final approval
Delivery to Stellantis
LCV PRO ONE RANGE wbt - update
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LCV Conversion Training Path - 2 VCT
Materials collection
Storyboarding
Graphic development
Final approval
Delivery to Stellantis
LCV CustomFit – VCT
Materials collection
| Storyboarding | [138 empty] | M
Graphic development
Final approval
Delivery to Stellantis
JEEP NEW COMPASS WBT - Part 2 (Barbirato)
Materials (first part)
| Storyboarding | [81 empty] | M | [6 empty] | M | [6 empty] | M
Articulate development
Final approval
Delivery to Stellantis
JEEP NEW COMPASS TTT Handodver Memento (Barbirato)
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
CONNECTED SERVICES - ExF - Exp wbt
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Avenger 4xe Recap and USPs – Capsule
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
Dodge Charger Daytona (D'Aquino)
Materials
Storyboarding
Articulate and PDF development
| Final approval | [192 empty] | M
Delivery to Stellantis
Leapmotor App focus – Capsule
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
JEEP WAGONEER S
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LEAPMOTOR B10 WBT
Materials (first part)
| Storyboarding | [136 empty] | M | [14 empty] | M
Articulate development
Final approval
Delivery to Stellantis
Leapmotor HV Battery - Showroom mode – Capsule
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
JEEP COMPASS PEDAGOGICAL KIT
Materials (first part)
Storyboarding
Final approval
TTT delivery
LEAPMOTOR B10 TTT
Materials (first part)
Storyboarding
Final approval
Delivery to Stellantis
F2X WBT TTT
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
NOME CORSO
Materials
Storyboarding
Brand PM review
Articulate development
Changes
Delivery
Orders opening
NOME CORSO
WBT - nome fornitore
MEMENTO - nome fornitore
BEEDEEZ - nome fornitore
HANDOVER - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
VCT - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
TTT - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
LEGENDA
HL
STRATTA
LOGOTEL
FORNITORE A
L | LAVORAZIONE
C | CONSEGNA OFFLINE
X | FINE CON SCORM