## PLANNING 2025
2025 COURSE PLANNING
KEY
Materials
Storyboarding
M | Meeting in progress
Articulate development
Final approval
Delivery to Stellantis
| Month | [17 empty] | JANUARY | [30 empty] | FEBRUARY | [27 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER | [29 empty] | OCTOBER | [30 empty] | NOVEMBER | [29 empty] | DECEMBER | [29 empty] | JANUARY 2026 | [31 empty] | FEBRUARY 2026 | [27 empty] | MARCH 2026 | [30 empty] | APRIL 2026
| Week |  |  |  | 52 | [6 empty] | 1 | [11 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12 | [6 empty] | 13 | [6 empty] | 14 | [6 empty] | 15 | [6 empty] | 16 | [6 empty] | 17 | [6 empty] | 18 | [6 empty] | 19 | [6 empty] | 20 | [6 empty] | 21 | [6 empty] | 22 | [6 empty] | 23 | [6 empty] | 24 | [6 empty] | 25 | [6 empty] | 26 | [6 empty] | 27 | [6 empty] | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32 | [6 empty] | 33 | [6 empty] | 34 | [6 empty] | 35 | [6 empty] | 36 | [6 empty] | 37 | [6 empty] | 38 | [6 empty] | 39 | [6 empty] | 40 | [6 empty] | 41 | [6 empty] | 42 | [6 empty] | 43 | [6 empty] | 44 | [6 empty] | 45 | [6 empty] | 46 | [6 empty] | 47 | [6 empty] | 48 | [6 empty] | 49 | [6 empty] | 50 | [6 empty] | 51 | [6 empty] | 52 | [6 empty] | 53
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 2 | 22 | 23 | 25 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3
|  | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | W | T | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | 1 | 2 | 3 | 4 | 5 | 6 | 7 | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S | M | Tu | W | Th | F | S | S
JEEP AVENGER part 2 WBT
Shooting
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Leapmotor Battery Management Update CAPSULE
Material
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
Fiat 600 ICE gasoline engine Street Launch Edition
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL K10 Salesmen Knowledge Check up
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL K9 Salesmen Knowledge Check up
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL X250 STRATEGY CAPSULE and VCT
Material
Storyboarding
Graphic development
Final approval
Delivery to Stellantis
JEEP AVENGER MCA
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LEAPMOTOR B05
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Abarth 600e Competizione capsule
Material
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
Lancia New Y ICE Engine
Material
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
FIAT TOPOLINO Capsule
Material
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
FIAT QUBO capsule
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
CONNECTED SERVICES exF - exP
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LEAPMOTOR B10 REEV
Material
Storyboarding
Articulate and video development
Final approval
Delivery to Stellantis
LEAPMOTOR INDUCTION
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL EOT capsule
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
STELLANTIS 8-YEARS WARRANTY WBT
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LCV taxation wbt
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
ALFA ROMEO FICILI speech – 8 languages
Material
Ficili speech recording
Video development
Final approval
Delivery to Stellantis
CONNECTED SERVICES LCV
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Fiat 500e & HYBRID MY26
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
EV FEATURES EXP & EXF capsules
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Fiat 600e & Fiat 600 Hybrid MY26
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
CONNECTED SERVICES EXP & EXF vct HL
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
exF and exP CONNECTED SERVICES activation process
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
SERVICE CONTRACTS
Material
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
JEEP COMPASS ALTITUDE capsule (capsule)
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
CONNECTED SERVICES APP MARKET (capsule)
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
JEEP 8 YEARS WARRANTY (capsule)
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
ALFA ROMEO JUNIOR MY26 (capsule)
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
LEAPMOTOR C10 AWD 899 V (capsule)
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
FIAT 500 HYBRID TORINO capsule
Materials (first part)
| Storyboarding | [269 empty] | M
Beedeez development
Final approval
Delivery to Stellantis
JEEP WAGONEER S
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
ALFA ROMEO NEW TONALE Part 2 Synthesia
Shooting
| Storyboarding | [136 empty] | M
Synthesia development
Final approval
Delivery to Stellantis
SALES METHOD
Materials (first part)
Paper version
Synthesia development
Translation and Articulate development
Final approval
Delivery to Stellantis
FIAT PROFESSIONAL NSP
Materials (first part)
| Storyboarding | [239 empty] | HOLIDAYS | [6 empty] | HOLIDAYS
Graphic development
Test development
Delivery to Stellantis
LCV Conversion Training Path - 2 VCT
Materials collection
Storyboarding
Graphic development
Final approval
Delivery to Stellantis
LCV CustomFit – VCT
Materials collection
| Storyboarding | [138 empty] | M
Graphic development
Final approval
Delivery to Stellantis
ALFA ROMEO NEW TONALE WBT 1
Materials (Instruction letter)
| Storyboarding | [136 empty] | M | [75 empty] | M
Articulate development
Final approval
Delivery to Stellantis
AMI HANDOVER
Materials (first part)
Storyboarding
Synthesia development
Final approval
Delivery to Stellantis
FIAT TRIS HANDOVER
Materials (first part)
Storyboarding
Synthesia development
Final approval
Delivery to Stellantis
Fiat 500 - 600 - Pandina new trim strategy (D'Aquino)
Materials
Storyboarding and Synthesia development
Capsule development
Final approval
Delivery to Stellantis
LANCIA 8 YEARS WARRANTY capsule
Materials
| Storyboarding | [136 empty] | M
Capsule development
Final approval
Delivery to Stellantis
ALFA ROMEO 8 YEARS WARRANTY capsule
Materials
| Storyboarding | [136 empty] | M
Capsule development
Final approval
Delivery to Stellantis
FIAT 8 YEARS WARRANTY capsule
Materials
| Storyboarding | [136 empty] | M
Capsule development
Final approval
Delivery to Stellantis
ALFA ROMEO NEW TONALE WBT 1
Materials (Instruction letter)
| Storyboarding | [136 empty] | M | [75 empty] | M
Articulate development
Final approval
Delivery to Stellantis
PUBLIC CHARGING (Lerch) Part 2 WBT
Instruction letter december 2024
Storyboarding
Articulate development
| Meeting in progress | [33 empty] | M
Final approval
Delivery to Stellantis
AMI WBT (D'Aquino)
Materials
| Storyboarding | [45 empty] | M | [11 empty] | M
| Articulate development | [107 empty] | M
Final approval
Delivery to Stellantis
JEEP NEW COMPASS WBT - Part 1 (Barbirato)
Instruction letter december 2024
| Storyboarding | [23 empty] | M | [6 empty] | M | [7 empty] | M |  | M | [16 empty] | M
Articulate development
Final approval
Delivery to Stellantis
LANCIA YPSILON HF WBT (Barbirato)
Instruction letter 2024/11/22
| Storyboarding | [25 empty] | M |  |  |  | M |  |  |  | M |  |  |  | M |  | M | [5 empty] | M
Articulate development
Final approval
Delivery to Stellantis
Fiat TRIS WBT
Material - January 29
| Storyboarding | [103 empty] | M | [13 empty] | M | [11 empty] | M | [15 empty] | M | [6 empty] | M
Articulate development
Final approval
Delivery to Stellantis
LCV PRO ONE RANGE wbt - update
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
JEEP NEW COMPASS WBT - Part 2 (Barbirato)
Materials (first part)
| Storyboarding | [81 empty] | M | [6 empty] | M | [6 empty] | M
Articulate development
Final approval
Delivery to Stellantis
JEEP NEW COMPASS TTT Handodver Memento (Barbirato)
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
CONNECTED SERVICES - ExF - Exp wbt
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
Avenger 4xe Recap and USPs – Capsule
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
Dodge Charger Daytona (D'Aquino)
Materials
Storyboarding
Articulate and PDF development
| Final approval | [192 empty] | M
Delivery to Stellantis
Leapmotor App focus – Capsule
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
LEAPMOTOR B10 WBT
Materials (first part)
| Storyboarding | [136 empty] | M | [14 empty] | M
Articulate development
Final approval
Delivery to Stellantis
Leapmotor HV Battery - Showroom mode – Capsule
Materials (first part)
Storyboarding
Beedeez development
Final approval
Delivery to Stellantis
JEEP COMPASS PEDAGOGICAL KIT
Materials (first part)
Storyboarding
Final approval
TTT delivery
LEAPMOTOR B10 TTT
Materials (first part)
Storyboarding
Final approval
Delivery to Stellantis
F2X WBT TTT
Materials (first part)
Storyboarding
Articulate development
Final approval
Delivery to Stellantis
NOME CORSO
Materials
Storyboarding
Brand PM review
Articulate development
Changes
Delivery
Orders opening
NOME CORSO
WBT - nome fornitore
MEMENTO - nome fornitore
BEEDEEZ - nome fornitore
HANDOVER - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
VCT - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
TTT - nome fornitore | bar: 21 21 to 22 22; 52 25 25 to 52 26 26; 52 28 28 to 52 29 29; 1 1 1; 1 4 4 to 1 5 5
LEGENDA
HL
STRATTA
LOGOTEL
FORNITORE A
L | LAVORAZIONE
C | CONSEGNA OFFLINE
X | FINE CON SCORM