## Slide 1
OPERATING SITUATION OF TRAINING PROJECTS
July 22nd 2025
Koinè s.n.c Via Fornasio, 5 - 10092 Beinasco (TO) ITALY
Phone: 011.397.10.99 - Mobile: 335.6896974
e-mail: koine@koine.it

## Slide 2
June accounting situation - PURCHASE ORDER 31381148
PURCHASE ORDER 31381148 |  |  | 1.249.650,00
Variable costs Q1 | 312.413,00 |  | 
Variable costs Q2 | 312.413,00 |  | 
Variable costs Q3 | 312.412,00 |  | 
Variable costs Q4 | 312.412,00 |  | 
TOTAL ORDER AMOUNT | 1.249.650,00 |  | 
INVOICES ISSUED |  |  | 
KOINE 012/2025 March |  |  | 4.800,00
KOINE 014/2025 April |  |  | 60.989,80
KOINE 018/2025 June |  |  | 246.623,20
Total amount Invoiced |  |  | 312.413,00
TOTAL AMOUNT OF PROJECTS COMPLETED |  |  | 315.830,20
Remaining amount to be Invoiced |  |  | 937.237,00
TOTAL AMOUNT OF PROJECTS IN PROGRESS TO BE INVOICED |  |  | 257.517,40
Can we invoice the Variable costs Q2 item | 312.413,00 ?

## Slide 3
Can we invoice the remaining | 119.250,00?
June accounting situation - PURCHASE ORDER 31381147
PURCHASE ORDER 31381147 |  | 238.500,00
KOINE 013/2025 March |  | 35.268,65
KOINE 015/2025 April |  | 12.288,66
KOINE 019/2025 May-June |  | 71.692,69
Total amount Invoiced |  | 119.250,00
Total amount from January to July |  | 105.988,93
Remaining amount to be Invoiced |  | 119.250,00
Total amount from August to December |  | 85.450,99

## Slide 4
June accounting resources situation - PURCHASE ORDER 31381147
Month | ACTIVITY | DAYS | COST X DAY (€) | TOTAL | MANAGER | PRICE (€)
January-February-March | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 1st quarter 2025 |  |  |  | 20.000,00
January-February-March | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 42 | 295,18 | 12.397,56 | D'Aquino | 15.268,26
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17 | 295,18 | 5.018,06 | D'Aquino | 5.018,06
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 20 | 363,53 | 7.270,60 | Barbirato | 7.270,60
April-May-June | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 2nd quarter 2025 |  |  |  | 20.000,00
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17+20+23 | 295,18 | 17.710,80 | D'Aquino | 17.710,80
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 17+20+20 | 363,53 | 20.721,21 | Barbirato | 20.721,21
 | Total amount up to JULY |  |  |  |  | 105.988,93
DETAIL - ACTIVITY DONE UNTIL JULY

## Slide 5
DETAIL - ACTIVITY TO BE DONE FROM AUGUST TO DECEMBER
Month | ACTIVITY | DAYS | COST X DAY (€) | TOTAL | MANAGER | PRICE (€)
August-September- | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 3rd quarter 2025 |  |  |  | 20.000,00
August-September- | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 6+22 | 295,18 | 8.265,04 | D'Aquino | 8.265,04
August-September- | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 6+22 | 363,53 | 10.178,84 | Barbirato | 10.178,84
October- November-December | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 4rd quarter 2025 |  |  |  | 20.000,00
October- November-December | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 23+18 | 295,18 | 12.102,38 | D'Aquino | 12.102,38
October- November-December | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 23+18 | 363,53 | 14.904,73 | Barbirato | 14.904,73
 | Total amount from August to December |  |  |  |  | 85.450,99
June accounting resources situation - PURCHASE ORDER 31381147