## Slide 1
OPERATING SITUATION OF TRAINING PROJECTS
July 22nd 2025
Koinè s.n.c Via Fornasio, 5 - 10092 Beinasco (TO) ITALY
Phone: 011.397.10.99 - Mobile: 335.6896974
e-mail: koine@koine.it

## Slide 2
June accounting situation
PURCHASE ORDER 31381148 |  |  | 1.249.650,00
Variable costs Q1 | 312.413,00 |  | 
Variable costs Q2 | 312.413,00 |  | 
Variable costs Q3 | 312.412,00 |  | 
Variable costs Q4 | 312.412,00 |  | 
TOTAL ORDER AMOUNT | 1.249.650,00 |  | 
INVOICES ISSUED |  |  | 
KOINE 012/2025 March |  |  | 4.800,00
KOINE 014/2025 April |  |  | 60.989,80
KOINE 018/2025 June |  |  | 246.623,20
Total amount invoiced |  |  | 312.413,00
TOTAL AMOUNT OF PROJECTS COMPLETED |  |  | 315.830,20
Remaining amount to be Invoiced |  |  | 937.237,00
TOTAL AMOUNT OF PROJECTS IN PROGRESS TO BE INVOICED |  |  | 257.517,40
Can we invoice the item Variable costs Q2 | 312.413,00 ?

## Slide 3
June accounting situation PURCHASE ORDER 31381148
PROJECTS COMPLETED | 
BARBIRATO | 
JEEP Avenger 4xe Recap and USPs | 1.000,00
Leapmotor focus App | 3.800,00
Leapmotor HV Battery | 1.000,00
2025 Connected Services Overall Update ExF Brands | 19.600,00
2025 Connected Services Overall Update ExP Brands | 14.500,00
New Compass part 2 | 14.100,00
Leapmotor B10 Launch WBT | 19.600,00
Lancia 8 years Warranty | 1.000,00
Alfa 33 Stradale | 1.000,00
AR Logo 115° Anniversary | 1.000,00
Connected Services ExP pill | 1.000,00
Connected Services ExF pill | 1.000,00
New Compass Pedagogical Kit with TTT | 74.500,00
Leapmotor B10 Pedagogical Kit with TTT | 74.500,00
Memo File x 33 Stradale Brand Ambassador | 2.700,00
Leapmotor C10 REEV Energy Modes VCT | 14.700,00
C10 REEV capsule | 1.000,00
C10 REEV video | 3.900,00
Jeep Renegade capsule | 1.000,00
Amount | 250.900,00
PROJECTS COMPLETED | 
D'AQUINO | 
Citroën Ami | 19.408,00
Stellantis ProOne Range | 6.481,80
FIAT PRO 3-WHEELER | 19.513,00
Dodge Charger Daytona | 19.527,40
Amount | 64.930,20
PROJECTS COMPLETED | 
TOTAL Variable costs Q1 amount | 312.413,00
AMOUNT INVOICED | 312.413,00
TOTAL AMOUNT OF PROJECTS COMPLETED | 315.830,20
LACKING AMOUNT | -3.417,20
5
9
10
3
4
8
12
15
18
19
21
22
24
25
28
29
16
17 20
1
14
2
13

## Slide 4
Can we invoice Variable costs Q2 | 312.413,00 ?
 | PROJECTS IN PROGRESS at July | 
 | BARBIRATO | 
11 | Jeep Wagoneer S Launch WBT | 18.900,00
26 | Jeep New Compass Handover Memento | 9.000,00
27 | Leapmotor B10 Handover Memento | 9.000,00
30 | Alfa Romeo 8 years Warranty | 1.000,00
44 | Alfa Romeo Tonale MCA | 18.200,00
45 | Connected Services i-DOUV | 1.000,00
46 | Jeep Avenger MY 26 & Safety update | 1.000,00
47 | Leapmotor C10 AWD 6 800v battery | 1.000,00
48 | Connected Services App Market | 1.000,00
 | Amount | 60.100,00
June accounting situation PURCHASE ORDER 31381148
PROJECTS IN PROGRESS | 
TOTAL Variable costs Q2 amount | 312.413,00
TOTAL AMOUNT OF PROJECTS IN PROGRESS TO BE INVOICED | 249.100,00
 | PROJECTS IN PROGRESS at July | 
 | D'AQUINO | 
6 | CustomFit WBT | 19.600,00
7 | Conversion Training Path 2 VCT | 39.200,00
31 | LCV Induction update | 29.400,00
32 | FIAT 500 trim strategy | 5.000,00
33 | Pandina trim strategy | 5.000,00
34 | FIAT 600 trim strategy | 5.000,00
35 | FIAT 8 years warranty | 1.000,00
36 | LCV connect services | 19.600,00
37 | LCV F2move pillars (FOUR) | 4.000,00
38 | LCV taxation wbt | 19.600,00
39 | Sales methods quick guide WBT | 19.600,00
40 | Sales methods quick guide BROCHURE | 6.000,00
41 | AMI Handover video + shooting | 9.000,00
41 | AMI Handover PILL | 1.000,00
42 | TRIS Handover memento | 1.000,00
43 | DODGE video shooting | 5.000,00
 | Amount | 189.000,00

## Slide 5
Can we invoice the remaining | 119.250,00?
June accounting situation PURCHASE ORDER 31381147
PURCHASE ORDER 31381147 |  | 238.500,00
KOINE 013/2025 March |  | 35.268,65
KOINE 015/2025 April |  | 12.288,66
KOINE 019/2025 May-June |  | 71.692,69
Total amount Invoiced |  | 119.250,00
Total amount from January to July |  | 105.988,93
Remaining amount to be Invoiced |  | 119.250,00
Total amount from August to December |  | 85.450,99

## Slide 6
June accounting situation PURCHASE ORDER 31381147
Month | ACTIVITY | DAYS | COST X DAY (€) | TOTAL | MANAGER | PRICE (€)
January-February-March | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 1st quarter 2025 |  |  |  | 20.000,00
January-February-March | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 42 | 295,18 | 12.397,56 | D'Aquino | 15.268,26
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17 | 295,18 | 5.018,06 | D'Aquino | 5.018,06
April | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 20 | 363,53 | 7.270,60 | Barbirato | 7.270,60
April-May-June | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 2nd quarter 2025 |  |  |  | 20.000,00
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 17+20+23 | 295,18 | 17.710,80 | D'Aquino | 17.710,80
May - June - July | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 17+20+20 | 363,53 | 20.721,21 | Barbirato | 20.721,21
 | Total amount up to JULY |  |  |  |  | 105.988,93
ACTIVITY DONE UNTIL JULY

## Slide 7
June accounting situation PURCHASE ORDER 31381147
ACTIVITY DONE FROM JULY TO DECEMBER
Month | ACTIVITY | DAYS | COST X DAY (€) | TOTAL | MANAGER | PRICE (€)
August-September- | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 3rd quarter 2025 |  |  |  | 20.000,00
August-September- | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 6+22 | 295,18 | 8.265,04 | D'Aquino | 8.265,04
August-September- | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 6+22 | 363,53 | 10.178,84 | Barbirato | 10.178,84
October- November-December | GOVERNANCE ACCOUNT MANAGEMENT ACTIVITY | 4rd quarter 2025 |  |  |  | 20.000,00
October- November-December | SENIOR PROJECT MANAGEMENT ACTIVITY (Lavinia Crivellari) | 23+18 | 295,18 | 12.102,38 | D'Aquino | 12.102,38
October- November-December | SENIOR PROJECT MANAGEMENT ACTIVITY (Stefano Genovesio) | 23+18 | 363,53 | 14.904,73 | Barbirato | 14.904,73
 | Total amount from August to December JULY |  |  |  |  | 85.450,99